## Sheet1
# | Status | C/S | Module | Item
| Unk | S | GameMap
| Unk | S | NPCEngine
| To Do | S | Actor | Create updatePosition() function which update's the actor's position based on current position, moveto position, and time elapsed. (See client Actor class render function)
| To Do | S | AIEngine | Implement Runnable?
| To Do | S | AIEngine | Infinite loop: iterate through all movable NPC. If position == moveto, generate new position & toggle nextDirection. Then call Actor's updatePosition() function.
| To Do | S | ClientHandler | Modify infinte loop to only allow moves once game has started.
| To Do | S | ClientHandler | Send remaining coutdown to client
| To Do | S | ClientHandler | When gamestate changes, transmit list of actors, including self
| To Do | S | ClientHandler | Modify opcode switch case for player move packet; move request should just set "moveto"
| To Do | S | ClientHandler | Before infinite loop loops, calculate new player position based upon time, check for collisions, process them using processCollision (verify return value in case of win -- if so set gamestate to gameover transmit gameover win, exit loop), transmit new location and health.
| To Do | S | ClientHandler | Transmit game over / loss when gamestate changes to gameover
| To Do | S | GlobalGameLogic | Add GAME_STATE enum with types for login, countdown, ingame, gameover
| To Do | S | GlobalGameLogic | Add int countdown, GAME_STATE state
| To Do | S | GlobalGameLogic | Add function setState(GAME_STATE state)
| To Do | S | GlobalGameLogic | Add function setCounter(int t)
| To Do | S | GlobalGameLogic | Add function checkCountdown()
| To Do | S | GlobalGameLogic | Add function checkState()
| To Do | S | GlobalGameLogic | Add function getGameDB()
| To Do | S | GlobalGameLogic | Add function getGameMap()
| To Do | S | GlobalGameLogic | Add function getNPCEngine()
| To Do | S | GlobalGameLogic | Add function getAIEngine()
| To Do | S | GlobalGameLogic | Remove function run() and do not implement Runnable
| To Do | S | Main | Modify infinite loop to only loop for 20 seconds after last client connects, then initiate 10 second countdown, set gamestate to countdown, accept no more clients.
| To Do | S | Main | Wait for all other threads to end before exiting and/or restarting
| To Do | S | NetworkStreamWriter | Function sentCredits(int credits) to transmit current credit load
| To Do | S | NetworkStreamWriter | Function sendHealth(int health) to transmit player health
| To Do | S | NetworkStreamWriter | Function sendEndGame(boolean win) to transmit game over with win/lose
| To Do | S | NetworkStreamWriter | Function sendNewActorData(Integer id) to transmit info for 'new' Actor
| To Do | S | NonPlayerCharacter | Update players with random location to use GameMap's getRandomMapPoint()
| To Do | S | NonPlayerCharacter | Add nextDirection enum {VERTICAL(-1), HORIZONTAL(1)}
| To Do | S | PlayerCharacter | Add int health, boolean inBridge, float distFromLastClass, float distFromLastEx, boolean sick, int credits, int lastClassAttended
| To Do | S | PlayerCharacter | Add function updateSpeed() which updates a player's speed based upon health
| To Do | S | PlayerCharacter | Extend Actor's updatePosition function to decrement distFromLastClass and distFromLastEx appropriately.
| To Do | S | PlayerCharacter | Add a processCollision(Integer id) function which handles collisions with all other objects. Update the following accordingly: health, speed, distFromLastClass, distFromLastEx, sick, credits. Return 1 if game won, 0 otherwise.
| To Do | S | Point2D | Implement moveTo (copy from client side)
| To Do | C | CoreGameLogic | In function setState, do not create self actor, but rather wait until actor list is transmitted during final countdown
| To Do | C | NetworkEngine | Add case to process player health, credit, endgame and newactordata packets
| To Do | C | NetworkStreamParser | Add function getHealth()
| To Do | C | NetworkStreamParser | Add function getGameOverState()
| To Do | C | NetworkStreamParser | Add function readActorInfo(Integer id)
| To Do | N | Protocol | Agree on packet info for health, credits, gameover, character (actor) info.
| To Do | D | Design Diagram | Make design diagram visually appealing
| To Do | D | Issue / Solution | Extend to include aforementioned functions.
| To Do | D | Prioritized Issues | Create once final project point is reached.
| To Do | D | User Documentation | Modify Creating a Game, #2 to reflect design - start game 30 seconds after last player connects.
| To Do | D | User Documentation | Modify / Remove Disconnecting, as this was not in the design and the method described in #1 is not a recommended method of disconecting.
| To Do | D | Work Logs | Continue updating
| To Do | O | Map | Create a graphical BU map
| To Do | O | Map | Create the map data image
| To Do | O | Map | Create a text file for NPCs on the map
| Done | S | GlobalGameDatabase
| Done | S | NetworkStreamParser
| Done | C | Actor
| Done | C | ActorEngine
| Done | C | AnimatedSprite
| Done | C | GameMap
| Done | C | LoadingScreen
| Done | C | LoginScreen
| Done | C | Main
| Done | C | NetworkStreamWriter
| Done | C | Point2D
| Done | C | UIEngine
| Done | C | Xcanvas
| Done | D | Requirements/Test Case
| Done | D | System Design

## Sheet2
Requirements | Test Cases
Server accepts client connections | When client requests connection, check that server sends map
Client can connect to server | Client generates login packet with username
Server distributes game map | After client connects and finishes "loading", see that map files are saved in app directory
Clientside user will have the ability to walk around map | After game loads, press up, down, left, and right arrow keys separately. Verify character moves accordingly.
Player will decrease health by interacting with virus and professors and eating unhealthily. | Walk around map and encounter Dunkin Doughnuts, Store 24, H1N1.
Player cannot attend classes while sick | After verifying previous test case, enter several classrooms and note that credits do not increase
Player can get well by going to SHS | After previous test cases, walk to SHS and enter door, continue into next test case.
Player can receive credit by attending class | After previous test cases, walk back to a classroom and enter it. Note credit increase.
Player cannot recieive credit for class twice in a row. | After attending a class, immediately return to the same class, note credits do not increase
Player can increase health by eating and exercising | After beginning game, walk to an eating establishment other than Dunkin Doughnuts or Store 24. Then proceed to FitRec. Note health increase both times.
Player wins by collecting 36 credits and going to Agganis | Attend class such that credits are numbered 36, walk to Agganis and enter. Note "Game Over"
Game ends when one player wins. | Connect 2 players, when one wins both receive "Game Over" message and are disconnected.
Server handles an unlimited numer of clients. | Start server, join first client. Once a client joins, have another client join within 30 seconds. Repeat infinitely.