## Sheet1
# | Status | C/S | Module | Item
| Done | C | Actor
| Done | C | ActorEngine
| Done | C | AnimatedSprite
| Done | C | GameMap
| Done | C | LoadingScreen
| Done | C | LoginScreen
| Done | C | Main
| Done | C | NetworkStreamWriter
| Done | C | Point2D
| Done | C | UIEngine
| Done | C | Xcanvas
| To Do | C | NetworkEngine | Add case to process player health, credit, endgame and newactordata packets
| To Do | C | NetworkStreamParser | Add function getHealth()
| To Do | C | NetworkStreamParser | Add function getCredits()
| To Do | C | NetworkStreamParser | Add function getWinner()
| To Do | C | NetworkStreamParser | Add function readActorInfo()
| To Do | C | CoreGameLogic | In function setState, do not create self actor, but rather wait until actor list is transmitted during final countdown
| Done | D | Requirements/Test Case
| Done | D | System Design
?? | To Do | D | Reference Documents | Function call reference - for each function, who calls it and what does it call?
JS | To Do | D | Schedule | Create a schedule akin to the one Mr. Keklak emailed out.
JS | To Do | D | Reference Documents | Mapping of NPCs to type numbers
JS | To Do | D | User Documentation | Modify / Remove Disconnecting, as this was not in the design and the method described in #1 is not a recommended method of disconecting.
JS | To Do | D | User Documentation | Modify Creating a Game, #2 to reflect design - start game 30 seconds after last player connects.
LW | To Do | D | Issue / Solution | Extend to include aforementioned functions.
LW | To Do | D | Design Diagram | Make design diagram visually appealing
| To Do | D | Work Logs | Continue updating
| To Do | D | Prioritized Issues | Create once final project point is reached.
GM | To Do | N | Protocol | Agree on packet info for health, credits, gameover, character (actor) info.
GM | To Do | O | Map
GM | To Do | O | Map | Create a text file for NPCs on the map
GM | To Do | O | Map | Create the map data image
X | Done | S | GlobalGameDatabase
X | Done | S | NetworkStreamParser
AV | Rem | S | ClientHandler | Transmit game over when gamestate changes to gameover (check winner)
AV | Rem | S | ClientHandler | Transmit new location, health, credits. (each loop)
AV | Rem | S | ClientHandler | Transmit other visible players when they move (each loop)
AV | To Do | S | PlayerCharacter | Add a processCollision(Integer id) function which handles collisions with all other objects. Update the following accordingly: health, speed, lastClass, distFromLastEx, sick, credits. Return 1 if game won, 0 otherwise.
AV | To Do | S | ClientHandler | Add datamember PlayerCharacter myCharacter, update setActorID to retrieve this
AV | To Do | S | PlayerCharacter | Add function Integer checkCollision() which checks to see if this player has collided with any other actor. If so, return that actor's ID. If not, return -1.
AV | To Do | S | PlayerCharacter | Add function updateSpeed() which updates a player's speed based upon health
AV | To Do | S | PlayerCharacter | Add int health, boolean inBridge, int lastClass, float distFromLastEx, boolean sick, int credits, int lastClassAttended
AV | To Do | S | NonPlayerCharacter | Add nextDirection enum {VERTICAL(-1), HORIZONTAL(1)}
AV | To Do | S | Actor | Create updatePosition() function which update's the actor's position based on current position, moveto position, and time elapsed. (See client Actor class render function) It should also update lastmovetime
AV | To Do | S | PlayerCharacter | Extend Actor's updatePosition function to decrement distFromLastClass and distFromLastEx appropriately.
AV | To Do | S | ClientHandler | Implement sendAllCharacters() which transmits the appropraite actors to the client. (e.g. those which need to be displayed: other player characters, H1N1, manholes) This uses NetworkStreamWriter's sendNewActorData(int id, int type, String name, Point2D pos)
AV | To Do | S | NonPlayerCharacter | Modify constructor to set move to equal to position.
AV | To Do | S | ClientHandler | Modify infinte loop to only allow moves once game has started. (Or make 2 loops - one that loops until state changes to countdown, then transmits actors and countdown. When countdown finishes, enter the loop that blocks for packets)
AV | To Do | S | ClientHandler | Modify opcode switch case for player move packet; move request should just set "moveto"
AV | To Do | S | ClientHandler | Send remaining coutdown to client
AV | To Do | S | NonPlayerCharacter | Update players with random location to use GameMap's getRandomMapPoint()
AV | To Do | S | ClientHandler | When gamestate changes to COUNTDOWN, transmit list of actors, including self
GM | To Do | S | NetworkStreamWriter | Function sendEndGame(String winner) to transmit game over with winner's name
GM | To Do | S | NetworkStreamWriter | Function sendHealth(int health) to transmit player health
GM | To Do | S | NetworkStreamWriter | Function sendNewActorData(int id, int type, String name, Point2D pos) to transmit info for 'new' Actor
GM | To Do | S | NetworkStreamWriter | Function sentCredits(int credits) to transmit current credit load
GM | To Do | S | Point2D | Implement boolean sameCell(Point2D other) which truncates (or casts to ints) the Xs and Ys before comparing
GM | To Do | S | Point2D | Implement floatGetMinDistance(Point2D other)
GM | To Do | S | Point2D | Implement moveTo (copy from client side)
GM | To Do | S | Main | Modify infinite loop to only loop for 20 seconds after last client connects, then initiate 10 second countdown, set gamestate to countdown, accept no more clients.
GM | To Do | S | Main | Wait for all other threads to end before exiting and/or restarting
JH | To Do | S | GlobalGameLogic | Add function checkCountdown()
JH | To Do | S | GlobalGameLogic | Add function GAME_STATE checkState(), boolean checkState(GAME_STATE s)
JH | To Do | S | GlobalGameLogic | Add function getGameDB()
JH | To Do | S | GlobalGameLogic | Add function getGameMap()
JH | To Do | S | GlobalGameLogic | Add function getNPCEngine()
JH | To Do | S | GlobalGameLogic | Add function getWinner()
JH | To Do | S | GlobalGameLogic | Add function setCounter(int t)
JH | To Do | S | GlobalGameLogic | Add function setState(GAME_STATE s)
JH | To Do | S | GlobalGameLogic | Add GAME_STATE enum with types for login, countdown, ingame, gameover
JH | To Do | S | GlobalGameLogic | Add int countdown, GAME_STATE state, String winner
JH | To Do | S | GlobalGameLogic | Implement function run() as specified in ServerGlobalGameLogicExplained
JH | To Do | S | NPCEngine | Implement generateNewPosition(Integer actorID)
JH | To Do | S | GameMap | Implement Point2D getrandomHorizontal(Point2D p) and getRandomVertical(Point2D p) which find a random valid map point along either the same veritcal or horizontal line as the given point
JH | To Do | S | NPCEngine | Update loadNPCsFromFile to alternate assigning a direction to movable NPCs when calling the construct (alternate -1, 1)
X | Unk | S | GameMap

## Sheet2
Requirements | Test Cases
Server accepts client connections | When client requests connection, check that server sends map
Client can connect to server | Client generates login packet with username
Server distributes game map | After client connects and finishes "loading", see that map files are saved in app directory
Clientside user will have the ability to walk around map | After game loads, press up, down, left, and right arrow keys separately. Verify character moves accordingly.
Player will decrease health by interacting with virus and professors and eating unhealthily. | Walk around map and encounter Dunkin Doughnuts, Store 24, H1N1.
Player cannot attend classes while sick | After verifying previous test case, enter several classrooms and note that credits do not increase
Player can get well by going to SHS | After previous test cases, walk to SHS and enter door, continue into next test case.
Player can receive credit by attending class | After previous test cases, walk back to a classroom and enter it. Note credit increase.
Player cannot recieive credit for class twice in a row. | After attending a class, immediately return to the same class, note credits do not increase
Player can increase health by eating and exercising | After beginning game, walk to an eating establishment other than Dunkin Doughnuts or Store 24. Then proceed to FitRec. Note health increase both times.
Player wins by collecting 36 credits and going to Agganis | Attend class such that credits are numbered 36, walk to Agganis and enter. Note "Game Over"
Game ends when one player wins. | Connect 2 players, when one wins both receive "Game Over" message and are disconnected.
Server handles an unlimited numer of clients. | Start server, join first client. Once a client joins, have another client join within 30 seconds. Repeat infinitely.